## Sheet1
Date | Name of Resource | Hours | Tasks Worked | Comments
[5 empty] | Development | Testing | Project Management
2015-12-10 | Backiaraj,Rajesh,Suganya | 20 | Database migrate and Design,chain and region mainteances pages,Home page design and excel flow chart design. |  | 18 | 0 | 2
2015-12-11 | Backiaraj,Rajesh,Suganya | 22 | user login,server check and configure.store procedure,index page design and forgot password. |  | 20 |  | 2
2015-12-12 | Backiaraj,Rajesh,Suganya | 22 | server configure and marketing page start,label type page,index page changes and user register form. |  | 21 |  | 1
2015-12-14 | Backiaraj,Rajesh,Suganya | 20 | login session and start integrate with new design,index page design issues,user register and forgot password issue. |  | 19 |  | 1
2015-12-15 | Backiaraj,Rajesh,Suganya | 20 | new design integrated and marketing region worked,login session issue,User type page worked. |  | 19 |  | 1
2015-12-16 | Backiaraj,Rajesh,Suganya | 20 | Admin system all the pages actions worked,Validation start working. |  | 19 |  | 1
2015-12-17 | Backiaraj,Rajesh,Suganya | 20 | Validation working for all pages,user page working,spelling issue changed. |  | 19 |  | 1
2015-12-18 | Backiaraj,Rajesh,Suganya | 16 | validations updated all pages,fold type and user mainteances pages worked. |  | 15 |  | 1
2015-12-21 | Backiaraj,Rajesh,Suganya | 12 | Vendor,vendor factory pages worked,shade,quality,martketin class,marketing group, end use pages worked. |  | 11 |  | 1
2015-12-22 | Backiaraj,Rajesh,Suganya | 12 | user,customer pages worked and uploaded.Start working on production page. |  | 11 |  | 1
2015-12-23 | Backiaraj,Rajesh,Suganya | 12 | Customer page updated,system admin menu price,price matrix,product group, delivery methods pages worked. |  | 11 |  | 1
2015-12-24 | Backiaraj,Rajesh,Suganya | 12 | Product page working,size,brand,care pages worked |  | 11 |  | 1
2015-12-25 | Backiaraj,Rajesh,Suganya | 12 | product,caution,country of origion,care,garment,fibre pages worked. |  | 11 |  | 1
2015-12-26 | Backiaraj,Rajesh,Suganya | 12 | Care Phrase page worked and uploaded to demo url. |  | 11 |  | 1
2015-12-28 | Backiaraj,Rajesh,Suganya | 12 | Place order page working,Testing issues fixed and updated. |  | 11 |  | 1
2015-12-29 | Backiaraj,Rajesh,Suganya | 12 | Place order,confirm order pages worked. |  | 11 |  | 1
2015-12-30 | Backiaraj,Rajesh,Suganya | 12 | Symbol,care set,size pages working. |  | 11 |  | 1
2015-12-31 | Backiaraj,Rajesh,Suganya | 12 | symbol,care set,size code and size pages updated in demo url. |  | 11 |  | 1
2016-01-04 | Backiaraj,Rajesh,Suganya | 12 | Link to size for products page working,place order start,symbol and size issues fixed. |  | 11 |  | 1
2016-01-05 | Backiaraj,Rajesh,Suganya | 12 | Size,Care set pages redesign working. |  | 11 |  | 1
2016-01-06 | Backiaraj,Rajesh,Suganya | 12 | Size page changes,Care set page redesign working. |  | 11 |  | 1
2016-01-07 | Backiaraj,Rajesh,Suganya | 12 | Size,Care set pages updated. |  | 11 |  | 1
2016-01-08 | Backiaraj,Rajesh,Suganya | 12 | Size,Care set integrating with place order page. |  | 11 |  | 1
2016-01-09 | Backiaraj,Rajesh,Suganya | 12 | Sizes and symbol images worked in place order page. |  | 11 |  | 1
2016-01-11 | Backiaraj,Rajesh,Suganya | 12 | Place order and other pages issues worked. |  | 11 |  | 1
2016-01-12 | Backiaraj,Rajesh,Suganya | 12 | Place order page additional care phrase,Garment,Fiber tabs newly added. |  | 11 |  | 1
2016-01-13 | Backiaraj,Rajesh,Suganya | 12 | Place order page new tabs added and changes worked. |  | 11 |  | 1
2016-01-14 | Backiaraj,Rajesh,Suganya | 4 | Place order page issues working. |  | 3 |  | 1
2016-01-18 | Backiaraj,Rajesh,Suganya | 12 | Place order care instructions and order insert working. |  | 11 |  | 1
2016-01-19 | Backiaraj,Rajesh,Suganya | 12 | Caution,copy right pages worked, place order page integrate these two tabs. |  | 11 |  | 1
2016-01-20 | Backiaraj,Rajesh,Suganya | 12 | view order page working. |  | 11 |  | 1
2016-01-21 | Backiaraj,Rajesh,Suganya | 12 | View order in single page, PDF print tab worked. |  | 11 |  | 1
2016-01-22 | Backiaraj,Rajesh,Suganya | 12 | PO Number unique worked in place order,Confirm order PDF Creation worked. |  | 11 |  | 1
2016-01-23 | Backiaraj,Rajesh,Suganya | 12 | Confirm order and mail sent worked,Update order working. |  | 11 |  | 1
2016-01-25 | Backiaraj,Rajesh,Suganya | 12 | Order Update page worked.place order page issues checking. |  | 11 |  | 1
2016-01-26 | Backiaraj,Rajesh,Suganya | 12 | Confirm order PDF Creation changed into dynamic format.update place order issues working. |  | 11 |  | 1
2016-01-27 | Backiaraj,Rajesh,Suganya | 12 | update place order changes worked. |  | 11 |  | 1
2016-01-28 | Backiaraj,Rajesh,Suganya | 12 | place, update,view orders pages worked.Cart Bag added to the top. |  | 11 |  | 1
2016-01-29 | Backiaraj,Rajesh,Suganya | 12 | Multi language issues working and data uploading. |  | 11 |  | 1
2016-02-01 | Backiaraj,Rajesh,Suganya | 12 | Variable data data checking, Dashboard page worked. Languages issue checked and uploaded. |  | 11 |  | 1
2016-02-02 | Backiaraj,Rajesh,Suganya | 12 | Variable data page working,Changes worked and updated. |  | 11 |  | 1
2016-02-03 | Backiaraj,Rajesh,Suganya | 12 | Variable data place order working,Changes working. |  | 11 |  | 1
2016-02-04 | Backiaraj,Rajesh,Suganya | 12 | Variable data place order working,Testing issues working. |  | 11 |  | 1
2016-02-05 | Backiaraj,Rajesh,Suganya | 12 | 3 types of orders listed in the cart,All other product place order worked. |  | 11 |  | 1
2016-02-06 | Backiaraj,Rajesh,Suganya | 12 | checkout page listed,Variable place order,update,view pages worked . |  | 11 |  | 1
2016-02-08 | Backiaraj,Rajesh,Suganya | 12 | checkout place order worked,product list changed and all other and variable issue working. |  | 11 |  | 1
2016-02-09 | Backiaraj,Rajesh,Suganya | 12 | New user login created, confirm mail and order status pages worked. |  | 11 |  | 1
2016-02-10 | Backiaraj,Rajesh,Suganya | 12 | order details display,change password and dashboard pages worked. |  | 11 |  | 1
2016-02-11 | Backiaraj,Rajesh,Suganya | 12 | Order list page tab view,chain page permissions,Size code deativate ,suspended for all pages worked. |  | 11 |  | 1
2016-02-12 | Backiaraj,Rajesh,Suganya | 12 | Link to customer worked in user, product pages.issues worked in order list and other pages. |  | 11 |  | 1
2016-02-15 | Backiaraj,Rajesh,Suganya | 12 | User form changed,Pending orders alert worked and pending orders list page created. |  | 11 |  | 1
2016-02-16 | Backiaraj,Rajesh,Suganya | 12 | Right menu.User permission and place order pages worked. |  | 11 |  | 1
2016-02-17 | Backiaraj,Rajesh,Suganya | 12 | Care place order changed,user permession worked. |  | 11 |  | 1
2016-02-18 | Backiaraj,Rajesh,Suganya | 12 | User permission update,Fabric display delete and care order insert worked |  | 11 |  | 1
2016-02-19 | Backiaraj,Rajesh,Suganya | 12 | Care set symbol,Fibre issue, user based order display worked. |  | 11 |  | 1
2016-02-20 | Backiaraj,Rajesh,Suganya | 12 | User based order list,Order status track pages worked. |  | 11 |  | 1
2016-02-22 | Backiaraj,Rajesh,Suganya | 12 | variable,all other orders inser worked,Confirmation mail worked all the stages.Order Dates worked. |  | 11 |  | 1
2016-02-23 | Backiaraj,Rajesh,Suganya | 12 | Site moved into demo url,Pending orders page worked. Import DAT file working. |  | 11 |  | 1
2016-02-24 | Backiaraj,Rajesh,Suganya | 12 | Variable data import from DAT file worked, Order details changed into tabs. |  | 11 |  | 1
2016-02-25 | Backiaraj,Rajesh,Suganya | 12 | Place order update working.Upload data list page and confirm orders list worked. |  | 11 |  | 1
2016-02-26 | Backiaraj,Rajesh,Suganya | 12 | Data upload with Du,SU files and list view worked. |  | 11 |  | 1
2016-02-29 | Backiaraj,Rajesh,Suganya | 12 | Data Upload DU,SU insert and update worked, list supplier name. |  | 11 |  | 1
2016-03-01 | Backiaraj,Rajesh,Suganya | 12 | Changes worked, Customer maintenance ,DU,SU Import ,Place order Finish/Continue worked. |  | 11 |  | 1
2016-03-02 | Backiaraj,Rajesh,Suganya | 12 | Issues working,Place order update issue checking. |  | 11 |  | 1
2016-03-03 | Backiaraj,Rajesh,Suganya | 12 | Place order update,view order issues ,Amend order and PDF page worked. |  | 11 |  | 1
2016-03-04 | Backiaraj,Rajesh,Suganya | 12 | Order update worked,view sale order and PDF creation worked. |  | 11 |  | 1
2016-03-05 | Backiaraj,Rajesh,Suganya | 12 | Order update start working,PDF page care section updated dynamic. |  | 11 |  | 1
2016-03-07 | Backiaraj,Rajesh,Suganya | 12 | PDF Dynamic,Sales order edit tabs working. |  | 11 |  | 1
2016-03-08 | Backiaraj,Rajesh,Suganya | 12 | Sales amend orders,Garment display for all pages and PDF address and menu active |  | 11 |  | 1
2016-03-09 | Backiaraj,Rajesh,Suganya | 12 | Testing for Aitech and Demo urls |  | 11 |  | 1
2016-03-10 | Backiaraj,Rajesh,Suganya | 12 | Region added,PDF region added as dynamic,Order images change and Order description updated. |  | 11 |  | 1
2016-03-11 | Backiaraj,Rajesh,Suganya | 12 | Product image issue fixed and working issues. |  | 11 |  | 1
2016-03-14 | Backiaraj,Rajesh,Suganya | 12 | Issues working and checking |  | 11 |  | 1
2016-03-15 | Backiaraj,Rajesh,Suganya | 12 | Changes working, and working the Date Picker. |  | 11 |  | 1
2016-03-16 | Backiaraj,Rajesh,Suganya | 12 | changes worked and date picker worked in checkout page. |  | 11 |  | 1
2016-03-17 | Backiaraj,Rajesh,Suganya | 12 | Chin permissions worked,Issues working and checked pages. |  | 11 |  | 1
2016-03-18 | Backiaraj,Rajesh,Suganya | 12 | Excel Export,Order search and Orser Status pages worked. |  | 11 |  | 1
2016-03-19 | Backiaraj,Rajesh,Suganya | 12 | Export Excel issue checked and updated.. |  | 11 |  | 1
2016-03-21 | Backiaraj,Rajesh,Suganya | 12 | Changes,issues and testing worked. |  | 11 |  | 1
2016-03-22 | Backiaraj,Rajesh,Suganya | 12 | Issues worked and new design checking for tha pages. |  | 11 |  | 1
2016-03-23 | Backiaraj,Rajesh,Suganya | 12 | Art work approved working,mail confirmation working. |  | 11 |  | 1
2016-03-24 | Backiaraj,Rajesh,Suganya | 12 | Artwork mail and order list status worked. |  | 11 |  | 1
2016-03-25 | Backiaraj,Rajesh,Suganya | 12 | mail list page and view page worked.Mail icons added all the order list page. |  | 11 |  | 1
2016-03-28 | Backiaraj,Rajesh,Suganya | 12 | All the mail list track working. |  | 11 |  | 1
2016-03-29 | Backiaraj,Rajesh,Suganya | 12 | Mail view page worked, Once approved and rejection mail status mail track |  | 11 |  | 1
2016-03-30 | Backiaraj,Rajesh,Suganya | 12 | Mail rejection comments added,changes worked in mail list page.Product list excel created and send mail |  | 11 |  | 1
2016-03-31 | Backiaraj,Rajesh,Suganya | 12 | mail time based process working, Start working on Cron jobs. |  | 11 |  | 1
2016-04-01 | Backiaraj,Rajesh,Suganya | 12 | cron job worked,Chain based database working. |  | 11 |  | 1
2016-04-02 | Backiaraj,Rajesh,Suganya | 12 | Chain and Super admin login pages working. |  | 11 |  | 1
2016-04-04 | Backiaraj,Rajesh,Suganya | 12 | Logged in pages worked,New chain creates and added in the DB |  | 11 |  | 1
2016-04-05 | Backiaraj,Rajesh,Suganya | 12 | Chain Update and Delete worked in the super admin. |  | 11 |  | 1
2016-04-06 | Backiaraj,Rajesh,Suganya | 12 | Chain Admin login pages working. |  | 11 |  | 1
2016-04-07 | Backiaraj,Rajesh,Suganya | 12 | Files moved into demo url and updated the admin system menu pages. |  | 11 |  | 1
2016-04-08 | Backiaraj,Rajesh,Suganya | 12 | Chain system admin menu pages working.Super admin system admin menus checking,. |  | 11 |  | 1
2016-04-11 | Backiaraj,Rajesh,Suganya | 12 | Changes working and integarting the Application menu pages. |  | 11 |  | 1
2016-04-12 | Backiaraj,Rajesh,Suganya | 12 | logo pages,application menus working,Dynamic folder creation worked. |  | 11 |  | 1
2016-04-13 | Backiaraj,Rajesh,Suganya | 12 | Dynamically folder creation worked ,Mail issue checking and uploaded the url. |  | 11 |  | 1
2016-04-14 | Backiaraj,Rajesh,Suganya | 12 | Dynamically folder creation and accessing from the chain worked, admin ,system ,application menu worked |  | 11 |  | 1
2016-04-15 | Backiaraj,Rajesh,Suganya | 12 | Data upload menu worked , placed the order |  | 11 |  | 1
2016-04-16 | Backiaraj,Rajesh,Suganya | 12 | Care Label view order,All other order update, view all other order pages worked. |  | 11 |  | 1
2016-04-18 | Backiaraj,Rajesh,Suganya | 12 | Sale place order,order list,view sale order pages worked. Chain create load issue worked. |  | 11 |  | 1
2016-04-19 | Backiaraj,Rajesh,Suganya | 12 | Confirm orders list pages worked,template menu display worked and user profile page worked. |  | 11 |  | 1
2016-04-20 | Backiaraj,Rajesh,Suganya | 12 | changes worked,Dunnes chain created and uploaded all the origional products and sizes. |  | 11 |  | 1
2016-04-21 | Backiaraj,Rajesh,Suganya | 12 | delivery instruction page changes worked,isssues working. |  | 11 |  | 1
2016-04-22 | Backiaraj,Rajesh,Suganya | 12 | issues worked and create new chain roots created and working. |  | 11 |  | 1
2016-04-25 | Backiaraj,Rajesh,Suganya | 12 | Roots chain content posting and changes worrked and updated. |  | 11 |  | 1
2016-04-26 | Backiaraj,Rajesh,Suganya | 12 | Roots content posted and sample orders worked for testing. |  | 11 |  | 1
2016-04-27 | Backiaraj,Rajesh,Suganya | 12 | Chain update and design issues worked. |  | 11 |  | 1
2016-04-28 | Backiaraj,Rajesh,Suganya | 12 | Roots login changes working for care lables order and delivery instruction popup worked. Tracking labels order pages working. |  | 11 |  | 1
2016-04-29 | Backiaraj,Rajesh,Suganya | 12 | Tracking lables order pages completed.uploaded all the file in live and tested. |  | 11 |  | 1
2016-04-30 | Backiaraj,Rajesh,Suganya | 12 | Tracking order mails pages,Delivery added order view page and testing the pages. |  | 11 |  | 1
2016-05-02 | Backiaraj,Rajesh,Suganya | 12 | Tested for roots,fixed the No size issue |  | 11 |  | 1
2016-05-03 | Backiaraj,Rajesh,Suganya | 12 | Testing for roots, All changes uploaded in the Unique super admin. Import file issue fixed. |  | 11 |  | 1
2016-05-05 | Backiaraj,Rajesh,Suganya | 12 | Roots chain Tracking labels order moved into sales order confirmation,Super admin create new chain added new changes |  | 11 |  | 1
2016-05-06 | Backiaraj,Rajesh,Suganya | 12 | Tracking order mails working for all order pages.alternative products code removed only in roots |  | 11 |  | 1
2016-05-09 | Backiaraj,Rajesh,Suganya | 12 | Checking tracking labels order and auto generate mail for artwork. |  | 11 |  | 1
2016-05-10 | Backiaraj,Rajesh,Suganya | 12 | Track label order changes worked. Track label products and label print colour added dynamic. |  | 11 |  | 1
2016-05-11 | Backiaraj,Rajesh,Suganya | 12 | Roots track label changes worked and updated..images cropped for roots careset(Tseries) |  | 11 |  | 1
2016-05-12 | Backiaraj,Rajesh,Suganya | 12 | worked all the changes for roots and careset images cropping. |  | 11 |  | 1
2016-05-13 | Backiaraj,Rajesh,Suganya | 12 | Updated symbols and caresets with new images.changes are done for care and all other products |  | 11 |  | 1
2016-05-14 | Backiaraj,Rajesh,Suganya | 12 | Roots chain tested and issue fixed. |  | 11 |  | 1
2016-05-17 | Backiaraj,Rajesh,Suganya | 12 | chages worked on care label,track and all other product orders. |  | 11 |  | 1
2016-05-18 | Backiaraj,Rajesh,Suganya | 12 | Care label fibre and garment compositions worked. |  | 11 |  | 1
2016-05-19 | Backiaraj,Rajesh,Suganya | 12 | update and vieworders worked for fibre and garment pages. Updated in live |  | 11 |  | 1
2016-05-20 | Backiaraj,Rajesh,Suganya | 12 | Place order fibre and garment changes worked and button postion issue checking. |  | 11 |  | 1
2016-05-23 | Backiaraj,Rajesh,Suganya | 12 | Fibre and garment component changes worked for update and view order. uploaded in live |  | 11 |  | 1
2016-05-24 | Backiaraj,Rajesh,Suganya | 12 | New changes worked and updated. |  | 11 |  | 1
2016-05-25 | Backiaraj,Rajesh,Suganya | 12 | Roots changes tested and issues worked, userlist prepared from old site and deliveryinstruction page worked for dunnes |  | 11 |  | 1
2016-05-26 | Backiaraj,Rajesh,Suganya | 12 | Place order header button alignment issue, Style No remain to all order and artwork content changed. |  | 11 |  | 1
2016-05-27 | Backiaraj,Rajesh,Suganya | 12 | Users added for roots and mail address assigned to Shirley.Casesenstive worked for Login |  | 11 |  | 1
2016-05-28 | Backiaraj,Rajesh,Suganya | 12 | Fibre & Garment change, production region dropdown, continue & addtocart change and Continue shopping button change |  | 11 |  | 1
2016-05-30 | Backiaraj,Rajesh,Suganya | 12 | Fibre&Garment changes worked in vieworders and viewsalesorder. Fibre&Garment alignment issue worked, Fibre&Garment changes and Previous, Next changes worked for Dunnes. |  | 11 |  | 1
2016-05-31 | Backiaraj,Rajesh,Suganya | 12 | Additional colour and style button worked for track&care labels.PO Number default worked for care,track and allother orders.Garment and Fibre changes worked |  | 11 |  | 1
2016-06-01 | Backiaraj,Rajesh,Suganya | 12 | Continus&addtocart status delete function worked.Remove dropdown and garment label for fibre.Set ponumber as readonly for care, track and allother.Added style&color show worked |  | 11 |  | 1
2016-06-02 | Backiaraj,Rajesh,Suganya | 12 | Garment Fibre, Garment Component button, Addtional styles worked for Fibre composition.Garment label changed in view orders |  | 11 |  | 1
2016-06-03 | Backiaraj,Rajesh,Suganya | 12 | Style No dropdown worked for carelabels and tracklabels.Additional style changes working |  | 11 |  | 1
2016-06-08 | Backiaraj,Rajesh,Suganya | 12 | changes worked for carelabel and tracking labels.Alignment changes worked for viewsales orders |  | 11 |  | 1
2016-06-09 | Backiaraj,Rajesh,Suganya | 12 | Fibre and garment issues worked for pdf and update order.Track order alignment worked for pdf |  | 11 |  | 1
2016-06-10 | Backiaraj,Rajesh,Suganya | 12 | Fibre and garment changes worked for amendorders.Changes tested and issues worked |  | 11 |  | 1
2016-06-11 | Backiaraj,Rajesh,Suganya | 12 | All the changes tested in roots. |  | 11 |  | 1
2016-06-13 | Backiaraj,Rajesh,Suganya | 12 | Changes tested and issues fixed. |  | 11 |  | 1
2016-06-14 | Backiaraj,Rajesh,Suganya | 12 | Pricematrix code checking. Style duplication issue worked. |  | 11 |  | 1
2016-06-15 | Backiaraj,Rajesh,Suganya | 12 | checkout list design changed,place order region and style no changes worked. |  | 11 |  | 1
2016-06-16 | Backiaraj,Rajesh,Suganya | 12 | Automatic style number change worked and changes tested. |  | 11 |  | 1
2016-06-17 | Backiaraj,Rajesh,Suganya | 12 | Fibre and garment changes worked. Resposive pages checking. |  | 11 |  | 1
2016-06-20 | Backiaraj,Rajesh,Suganya | 12 | Responsive tested and design issues worked. |  | 11 |  | 1
2016-06-21 | Backiaraj,Rajesh,Suganya | 12 | Responsive tested and design issues worked (Dashboard,Usertype maintenance, Product maintenance, Care set maintenance, Print invoice, Viewordet and Viewsalesorder and Care Place Order) |  | 11 |  | 1
2016-06-22 | Backiaraj,Rajesh,Suganya |  | Font awesome icon added to Add,Delete and View for all pages.Responsive issue worked. (completed order page - ordertrack alignment, view icon issue, amendorders.) |  | 11 |  | 1
2016-06-23 | Backiaraj,Rajesh,Suganya | 12 | Fibre&Garment, Check out page changes worked for Dunnes. Responsive tested and issues working. |  | 11 |  | 1
2016-06-24 | Backiaraj,Rajesh,Suganya | 12 | Font awesome icon added for all pages in Dunnes, responsive tested and issues worked for Dunnes. |  | 11 |  | 1
2016-06-25 | Backiaraj,Rajesh,Suganya | 12 | Pricematrix file upload and view ,Responsive issues worked for dunnel and roots |  | 11 |  | 1
2016-06-27 | Backiaraj,Rajesh,Suganya | 12 | Next, Previuos button issue worked in care,track,variable and allother products for roots and Dunnes. Pricematrix worked in viewsalesorder for roots |  | 11 |  | 1
2016-06-29 | Backiaraj,Rajesh,Suganya | 12 | Care set images cropped and uploaded in caresetmaintenance for roots. Care set image alignment worked for carelabes, updateorder,checkout, viewsalesorder and printinvoice. |  | 11 |  | 1
2016-06-30 | Backiaraj,Rajesh,Suganya | 12 | Fibre and Garment component issue, season and color validation worked for roots. Multiple file upload worked in artwork page. |  | 11 |  | 1
2016-07-01 | Backiaraj,Rajesh,Suganya | 12 | Add Style button changes worked for carelabel, Fibre&Garment delete button changes worked. |  | 11 |  | 1
2016-07-04 | Backiaraj,Rajesh,Suganya | 12 | StyleNo added in Careset an Fibre tab, Delete button and Style changes worked for update order. Pricematrix table worked. |  | 11 |  | 1
2016-07-05 | Backiaraj,Rajesh,Suganya | 12 | Invoice address, delivery address, suppliercode changes worked for Usermaintenance, Customermaintenance. Customer/Vendor Order Number, Delivert To, Bill to address worked for delivery instruction |  | 11 |  | 1
2016-07-06 | Backiaraj,Rajesh,Suganya | 12 | Usermaintenance, Customermaintenance, Deliverysucharge page changes worked. Ponumber changes worked in place order. |  | 11 |  | 1
2016-07-07 | Backiaraj,Rajesh,Suganya | 12 | Customer name and company name changes worked in all the view page and order list page. fibre search worked for place order |  | 11 |  | 1
2016-07-08 | Backiaraj,Rajesh,Suganya | 12 | User details and customer details added to roots. |  | 11 |  | 1
2016-07-11 | Backiaraj,Rajesh,Suganya | 12 | Link to customer for multiple products worked in productmaintenance, price matrix worked for artwork upload. |  | 11 |  | 1
2016-07-12 | Backiaraj,Rajesh,Suganya | 12 | Artwork upload email session worked for pricematrix and maillist attachment image worked. |  | 11 |  | 1
2016-07-13 | Backiaraj,Rajesh,Suganya | 12 | Pricematrix table design worked for email, style delete button issue worked for care label and still to complete button validation worked |  | 11 |  | 1
2016-07-14 | Backiaraj,Rajesh,Suganya | 12 | Price Ex(China) label and Order Id label changes worked, Invoice Price Confirm changes worked in activation page and artwork approval link checked.Artwork multiple product add and link to sent mail. |  | 11 |  | 1
2016-07-15 | Backiaraj,Rajesh,Suganya | 12 | Artwork upload mail system, artwork approval status worked and Order Track view status worked |  | 11 |  | 1
2016-07-18 | Backiaraj,Rajesh,Suganya | 12 | Variable data image, minimum price $50 change, Production region change, Remove Price quantity from Artwork approval mail change and Pricing confirmation tab add worked for roots. |  | 11 |  | 1
2016-07-19 | Backiaraj,Rajesh,Suganya | 12 | Price matrix approval and rejection worked. Rejected order and view rejected orders worked for co ordinator |  | 11 |  | 1
2016-07-20 | Backiaraj,Rajesh,Suganya | 12 | Status buttons (Approve and Reject) worked for price approval and artwork approval mail, Country of origin changes worked, Variable data image worked and Updated user list prepared |  | 11 |  | 1
2016-07-21 | Backiaraj,Rajesh,Suganya | 12 | Artwork upload and price matrix system tested and issues worked, From address changed as dyanamic for all mail system. Track price matrix is working |  | 11 |  | 1
2016-07-22 | Backiaraj,Rajesh,Suganya | 12 | StyleNumber and PO Number changes worked in artwork upload and attachement, artwork status issue, track order issue worked, track price matrix uploaded. |  | 11 |  | 1
2016-07-23 | Backiaraj,Rajesh,Suganya | 12 | Delivery date changes and approval and rejection mail list worked. View maillist attachment issue worked. |  | 11 |  | 1
2016-07-25 | Backiaraj,Rajesh,Suganya | 12 | place order validation issue worked for fibre composition delete button and still to complete button. Mail list worked for price resent process. Validation issue worked for Addtional style and Additional color buttons. |  | 11 |  | 1
2016-07-26 | Backiaraj,Rajesh,Suganya | 12 | Delivery date grey out change and track style popup change worked. Popup close button issue worked for all the pages. |  | 11 |  | 1
2016-07-27 | Backiaraj,Rajesh,Suganya | 12 | Page reload issue fixed for roots. Carelabel, allother product changes worked for Dunnes. Care Instructions added. |  | 11 |  | 1
2016-07-28 | Backiaraj,Rajesh,Suganya | 12 | Fibre compostion checkbox changes worked. Exclusive trim and exclusive decoration added in checkout page. |  | 11 |  | 1
2016-07-29 | Backiaraj,Rajesh,Suganya | 12 | Garment and Fibre checkbox changes worked for updateorders. Products added for Dunnes. |  | 11 |  | 1
2016-08-01 | Backiaraj,Rajesh,Suganya | 12 | Exclusive imformation and Fibre composition changes worked for viewsalesorder,amendorder and printinvoice |  | 11 |  | 1
2016-08-02 | Backiaraj,Rajesh,Suganya | 12 | Link size to product, List all the Office/Region and Variable data products changes worked. |  | 11 |  | 1
2016-08-03 | Backiaraj,Rajesh,Suganya | 12 | Popup close button(page reload) issue worked for all the pages in Dunnes. |  | 11 |  | 1
2016-08-04 | Backiaraj,Rajesh,Suganya | 12 | Users(adrian and emma as customer) added, changes tested in Dunnes. |  | 11 |  | 1
2016-08-05 | Backiaraj,Rajesh,Suganya | 12 | Product image changes, Variable data products table changes, Delivery instruction changes worked for Dunnes. |  | 11 |  | 1
2016-08-06 | Backiaraj,Rajesh,Suganya | 12 | Artwork upload process, Price Confirmation and mail system worked for Dunnes |  | 11 |  | 1
2016-08-08 | Backiaraj,Rajesh,Suganya | 12 | Uploaded all the changes in Dunnes and tested. |  | 11 |  | 1
2016-08-09 | Backiaraj,Rajesh,Suganya | 12 | Product image worked in printinvoice and ordering system tested. |  | 11 |  | 1
2016-08-10 | Backiaraj,Rajesh,Suganya | 12 | Upload artwork process, mailing list uploaded and tested for Dunnes |  | 11 |  | 1
2016-08-11 | Backiaraj,Rajesh,Suganya | 12 | Artwork upload, mailing system tested. From address changed dyanamically. |  | 11 |  | 1
2016-08-12 | Backiaraj,Rajesh,Suganya | 12 | Product image alignment, Color Description changes worked. Variable data product worked for artwork upload |  | 11 |  | 1
2016-08-16 | Backiaraj,Rajesh,Suganya | 12 | Pricematrix confirm worked for coordinator login |  | 11 |  | 1
2016-08-17 | Backiaraj,Rajesh,Suganya | 12 | Size quantity textbox, Product image alignment and priceapproval worked for Dunnes |  | 11 |  | 1
2016-08-18 | Backiaraj,Rajesh,Suganya | 12 | Pricematrix changes worked for care labels, variable data products and all other products. |  | 11 |  | 1
2016-08-19 | Backiaraj,Rajesh,Suganya | 12 | Price calculation, all other products worked for mail system and tested. |  | 11 |  | 1
2016-08-20 | Backiaraj,Rajesh,Suganya | 12 | Price calculation, MOQ and '$' to '£' changes worked for pricematrix system |  | 11 |  | 1
2016-08-22 | Backiaraj,Rajesh,Suganya | 12 | Artwork and price approval mail system worked and tested |  | 11 |  | 1
2016-08-23 | Backiaraj,Rajesh,Suganya | 12 | variable data quantity, ticket type, currency type changes worked |  | 11 |  | 1
2016-08-24 | Backiaraj,Rajesh,Suganya | 12 | Roots fibre and garment list updated. Artwork and Price nag box, ticke type price calculation worked for Dunnes. |  | 11 |  | 1
2016-08-25 | Backiaraj,Rajesh,Suganya | 12 | Ticket type table stack, ticket type price approve and reject worked in rejectedorders and viewsales order. |  | 11 |  | 1
2016-08-26 | Backiaraj,Rajesh,Suganya | 12 | Price matrix calculation, ticket type price worked and tested for Dunnes |  | 11 |  | 1
2016-08-29 | Backiaraj,Rajesh,Suganya | 12 | Price matrix displayed in viewsales order page (production and delivery login). |  | 11 |  | 1
2016-08-30 | Backiaraj,Rajesh,Suganya | 12 | Artwork approval and price matrix system tested for Dunnes. |  | 11 |  | 1
2016-08-31 | Backiaraj,Rajesh,Suganya | 12 | Font awesome icon added for all the buttons, alignment isssue worked. |  | 11 |  | 1
2016-09-01 | Backiaraj,Rajesh,Suganya | 12 | Price label, radio button for artwork and price approve, rejected moving button changes worked for roots |  | 11 |  | 1
2016-09-02 | Backiaraj,Rajesh,Suganya | 12 | Price round off, price table for viewsalesorder and printinvoice changes worked |  | 11 |  | 1
2016-09-03 | Backiaraj,Rajesh,Suganya | 12 | All other save order process worked for Dunnes. Users (Vicky, Qiong 1 , Qiong 2) added in roots |  | 11 |  | 1
2016-09-05 | Backiaraj,Rajesh,Suganya | 12 | Variable data product save order process worked for Dunnes |  | 11 |  | 1
2016-09-06 | Backiaraj,Rajesh,Suganya | 12 | Care label save order process worked for Dunnes and uploaded. |  | 11 |  | 1
2016-09-07 | Backiaraj,Rajesh,Suganya | 12 | Save order design issue worked and unique system moved to live. |  | 11 |  | 1
2016-09-08 | Backiaraj,Rajesh,Suganya | 12 | Price table worked for roots. Roots and Dunnes system moved to live |  | 11 |  | 1
2016-09-09 | Backiaraj,Rajesh,Suganya | 12 | Care, Track and all other save order worked for Roots. Roots User login tested in live. |  | 11 |  | 1
2016-09-12 | Backiaraj,Rajesh,Suganya | 12 | Save order and price round off changes uploaded and tested. |  | 11 |  | 1
2016-09-13 | Backiaraj,Rajesh,Suganya | 12 | Save icon, pagination issue worked. Saved order and price round off tested in live |  | 11 |  | 1
2016-09-14 | Backiaraj,Rajesh,Suganya | 12 | Multiple time save, previous, next, finish button change worked and uploaded in live. |  | 11 |  | 1
2016-09-15 | Backiaraj,Rajesh,Suganya | 12 | Auto save worked for saved orders and save icon changed. |  | 11 |  | 1
2016-09-16 | Backiaraj,Rajesh,Suganya | 12 | Multiple time save worked for Dunnes. Auto save order worked for roots and uploaded in live. |  | 11 |  | 1
2016-09-17 | Backiaraj,Rajesh,Suganya | 12 | Fibre component issue and auto save label changes worked for roots. |  | 11 |  | 1
2016-09-19 | Backiaraj,Rajesh,Suganya,Chinnadurai | 12 | Login page design worked and uploaded. Print color, care code, Vendor number and Order No changes worked. |  | 11 |  | 1
2016-09-20 | Backiaraj,Rajesh,Suganya | 12 | Login page changed for roots and dunnes, changes tested in roots. Activation page design worked. |  | 11 |  | 1
2016-09-21 | Backiaraj,Rajesh,Suganya | 12 | Rejection, Price approval, and price rejection design worked. Fibre composition issue worked. Auto save uploaded in roots. |  | 11 |  | 1
2016-09-22 | Backiaraj,Rajesh,Suganya,Rajesh kannan | 12 | Login page changed in live site(theuniquegroup.com). Design issue fixed for pendingorderlist, orderlist, completedlist,openorderlist. Delete button issue fixed fibre composition. |  | 11 |  | 1
2016-09-26 | Backiaraj,Rajesh,Suganya | 12 | Auto save and Order Id change worked for Dunnes and uploaded in live. |  | 11 |  | 1
2016-09-27 | Backiaraj,Rajesh,Suganya | 12 | uniquegroup site responsive issue worked. User login checked in unique site. |  | 11 |  | 1
2016-09-28 | Backiaraj,Rajesh,Suganya | 12 | sage acoount integeration checked |  | 11 |  | 1
2016-09-29 | Backiaraj,Rajesh,Suganya | 12 | uniquegroup site change updated in Bigbucket. Design, add style issues worked. |  | 11 |  | 1
2016-09-30 | Backiaraj,Rajesh,Suganya | 12 | uniquegroup site menu change design worked |  | 11 |  | 1
2016-10-01 | Backiaraj,Rajesh,Suganya | 12 | Uniquegroup menu issues fixed and updated in Bigbucket |  | 11 |  | 1
2016-10-03 | Backiaraj,Rajesh,Suganya | 12 | Price acknowledgement is working in coordinator login for roots . |  | 11 |  | 1
2016-10-04 | Backiaraj,Rajesh,Suganya | 12 | Price matrix email system worked in coordinator login for roots |  | 11 |  | 1
2016-10-05 | Backiaraj,Rajesh,Suganya | 12 | Price approval for customer and acknowledgement flow worked |  | 11 |  | 1
2016-10-06 | Backiaraj,Rajesh,Suganya | 8 | Woven label,Printed labels and Hangtag added in test site for roots |  | 11 |  | 1
2016-10-07 | Backiaraj,Rajesh,Suganya | 8 | Coming soon page for Woven label,Printed labels, Hangtag and Other products. Username and password amend. Login page for “URL” direction |  | 11 |  | 1
2016-10-10 | Backiaraj,Rajesh,Suganya | 8 | Login page for “URL” direction worked for roots. Menu issue checked. |  | 11 |  | 1
2016-10-11 | Backiaraj,Rajesh,Suganya | 8 | Login page for “URL” direction worked for Dunnes. Logout redirection worked. |  | 11 |  | 1
2016-10-12 | Backiaraj,Rajesh,Suganya | 8 | Menu changes worked. Login page redirect buffer issue working. |  | 11 |  | 1
2016-10-13 | Backiaraj,Rajesh,Suganya | 8 | Login page for “URL” direction worked and uploaded in test site. |  | 11 |  | 1
2016-10-14 | Backiaraj,Rajesh,Suganya | 8 | Stretch Reflective Material image changes, Login page redirection issue worked. |  | 11 |  | 1
2016-10-15 | Backiaraj,Rajesh,Suganya | 8 | Login page for “URL” direction uploaded in roots and Dunnes. Stretch Reflective Material image changed. |  | 11 |  | 1
2016-10-17 | Backiaraj,Rajesh,Suganya | 8 | Register user and forgot password worked for login page. User login checked. |  | 11 |  | 1
2016-10-18 | Backiaraj,Rajesh,Suganya | 8 | Google Analytics checked for theuniquegroup site. Register user and forgot password uploaded in live. |  | 11 |  | 1
2016-10-19 | Backiaraj,Rajesh,Suganya | 8 | jetpack plugin and Google Analytics checked for theuniquegroup site. |  | 11 |  | 1
2016-10-20 | Backiaraj,Rajesh,Suganya | 8 | Ip address and location tracker (plugin) checked and mail structure worked for Register user and forgot password . |  | 11 |  | 1
2016-10-21 | Backiaraj,Rajesh,Suganya | 8 | mail structure worked all the emails(place,confirm,artwork, production and delivery) |  | 11 |  | 1
2016-10-24 | Backiaraj,Rajesh,Suganya | 8 | Adding the User to the Customer maintenance and User registration with all the user filled in information worked. |  | 11 |  | 1
2016-10-25 | Backiaraj,Rajesh,Suganya | 8 | User details(supplier name&code,addrress,chain name,email and phone number) autofill from customer maintenance, forgot password and user registration mail worked. |  | 11 |  | 1
2016-10-26 | Backiaraj,Rajesh,Suganya | 8 | Register user list for Jackie's login worked for roots. Email template worked for Dunnes. |  | 11 |  | 1
2016-10-27 | Backiaraj,Rajesh,Suganya | 8 | username/password information mail worked for roots. Jackie user removed and Sai Nabar user added. |  | 11 |  | 1
2016-11-01 | Backiaraj,Rajesh,Suganya | 8 | Add and reject user worked in register user for roots |  | 11 |  | 1
2016-11-02 | Backiaraj,Rajesh,Suganya | 8 | Supplier assign to a use, add and reject user worked in register user for Dunnes |  | 11 |  | 1
2016-11-03 | Backiaraj,Rajesh,Suganya | 8 | User profile edit, add/reject user popup worked for roots and dunnes. |  | 11 |  | 1
2016-11-04 | Backiaraj,Rajesh,Suganya | 8 | Activate, Deactivate and delete popup worked for roots. |  | 11 |  | 1
2016-11-07 | Backiaraj,Rajesh,Suganya | 8 | Order Summary page,email to sai, email message worked for roots. |  | 11 |  | 1
2016-11-08 | Backiaraj,Rajesh,Suganya | 8 | Roots online master list excel worked in order summary page for roots. |  | 11 |  | 1
2016-11-09 | Backiaraj,Rajesh,Suganya | 8 | changes(order summary table,multiple product id) worked for roots. |  | 11 |  | 1
2016-11-10 | Backiaraj,Rajesh,Suganya | 8 | Changes (Printed Label (Add the MLCN),breadcrumbs, populate printed label) and product id issue worked for roots. |  | 11 |  | 1
2016-11-11 | Backiaraj,Rajesh,Suganya | 8 | Printedlabel(edit,delete,view,confirm), Product add(Woven label and Hangtag) worked for roots. |  | 11 |  | 1
2016-11-12 | Backiaraj,Rajesh,Suganya | 8 | Price matrix,Artwork approval worked in printedlabel for roots |  | 11 |  | 1
2016-11-14 | Backiaraj,Rajesh,Suganya | 8 | Auto save, printinvoice worked in printedlabel for roots. |  | 11 |  | 1
2016-11-15 | Backiaraj,Rajesh,Suganya | 8 | Changes(adding season, adding woven,hangtag,other products) worked in all the pages for roots. |  | 11 |  | 1
2016-11-16 | Backiaraj,Rajesh,Suganya | 8 | Woven labels and hangtag flow(add, edit, view and confirm) worked for roots |  | 11 |  | 1
2016-11-17 | Backiaraj,Rajesh,Suganya | 8 | Other products flow(add, edit, view and confirm) and ordersummary page worked for roots. |  | 11 |  | 1
2016-11-18 | Backiaraj,Rajesh,Suganya | 8 | Order summary, check out and all the order page(ponumber,region remaining ) issues worked for roots. |  | 11 |  | 1
2016-11-21 | Backiaraj,Rajesh,Suganya | 8 | Amend/Cancel order worked in printed,woven,hangtag for roots. |  | 11 |  | 1
2016-11-22 | Backiaraj,Rajesh,Suganya | 8 | Product image oin checkout page, Ordersummay(table),Season(validation) worked for roots. |  | 11 |  | 1
2016-11-23 | Backiaraj,Rajesh,Suganya | 8 | Dashboard page image and issues worked for roots. Order summary page worked for Dunnes. |  | 11 |  | 1
2016-11-24 | Backiaraj,Rajesh,Suganya | 8 | Changes tested and issues fixed for roots. |  | 11 |  | 1
2016-11-25 | Backiaraj,Rajesh,Suganya | 8 | Order Summary excel, activate/reject page issues worked for roots. |  | 11 |  | 1
2016-11-26 | Backiaraj,Rajesh,Suganya | 8 | Price matrix table worked for woven,hangtag and other products for roots. |  | 11 |  | 1
2016-11-28 | Backiaraj,Rajesh,Suganya | 8 | Issues tested and sage acoount integeration checked for roots. |  | 11 |  | 1
2016-11-29 | Backiaraj,Rajesh,Suganya | 8 | Alertbox(sweet alert) changes is worked in all pages for roots. |  | 11 |  | 1
2016-11-30 | Backiaraj,Rajesh,Suganya | 8 | Checkout page delete button(popup) worked and tested for roots. |  | 11 |  | 1
2016-12-01 | Backiaraj,Rajesh,Suganya | 8 | Product image(printed,woven,hangtag,othe product) and Amend order(before 48hrs) changes worked. |  | 11 |  | 1
2016-12-02 | Backiaraj,Rajesh,Suganya | 8 | Flow for the woven/Hangtags/Printed label and Otherproducts, Accounts login and add Users(Mandyzhang,Jenny and shirl) worked for roots. |  | 11 |  | 1
2016-12-05 | Backiaraj,Rajesh,Suganya | 8 | Price disable,account confirm and delivery login changes worked for roots. |  | 11 |  | 1
2016-12-07 | Backiaraj,Rajesh,Suganya | 8 | Changes tested and quickbook online integration checked for roots. |  | 11 |  | 1
2016-12-08 | Backiaraj,Rajesh,Suganya | 8 | Care,Tracking label image changed and quickbook online integration checked for roots. |  | 11 |  | 1
2016-12-09 | Backiaraj,Rajesh,Suganya | 8 | Quickbook web conncetor checked in quickbook online for roots. |  | 11 |  | 1
2016-12-10 | Backiaraj,Rajesh,Suganya | 8 | Company, item, invoice added using api in Quickbook online for roots. |  | 11 |  | 1
2016-12-12 | Backiaraj,Rajesh,Suganya | 8 | Quickbook enterprise 16.0 integration checked for roots. |  | 11 |  | 1
2016-12-13 | Backiaraj,Rajesh,Suganya | 8 | QuickBooks desktop integration with php checked for roots. |  | 11 |  | 1
2016-12-14 | Backiaraj,Rajesh,Suganya | 8 | Invoice Import and export using Zed axis tool checked for roots. |  | 11 |  | 1
2016-12-15 | Backiaraj,Rajesh,Suganya | 8 | Invoice export(in excel) worked in accounts login for roots. |  | 11 |  | 1
2016-12-16 | Backiaraj,Rajesh,Suganya | 8 | Invoice excel imported and invoice structure changed in Quickbooks for roots. |  | 11 |  | 1
2016-12-19 | Backiaraj,Rajesh,Suganya | 8 | Excel export worked in online ordering system for roots. |  | 11 |  | 1
2016-12-20 | Backiaraj,Rajesh,Suganya | 8 | Product export and import list worked for roots. |  | 11 |  | 1
2016-12-21 | Backiaraj,Rajesh,Suganya | 8 | Product list excel file upload worked for roots. |  | 11 |  | 1
2016-12-22 | Backiaraj,Rajesh,Suganya | 8 | Invoice menu(Export and search) worked in separate login for roots. |  | 11 |  | 1
2016-12-23 | Backiaraj,Rajesh,Suganya | 8 | Exported list view table worked in invoice export for roots |  | 11 |  | 1
2016-12-24 | Backiaraj,Rajesh,Suganya | 8 | Invoice export login and issue worked in invoice export for roots |  | 11 |  | 1
2016-12-26 | Backiaraj,Rajesh,Suganya | 8 | Invoice excel export changes and issue worked for roots |  | 11 |  | 1
2016-12-27 | Backiaraj,Rajesh,Suganya | 8 | Invoice excel export changes tested and issue worked for roots |  | 11 |  | 1
2016-12-28 | Backiaraj,Rajesh,Suganya | 8 | Quickbook connection with zed axis checked and changes tested for roots. |  | 11 |  | 1
2016-12-29 | Backiaraj,Rajesh,Suganya | 8 | Search invoice and export invoice menu worked and zed axix conncetion issue checked for roots. |  | 11 |  | 1
2016-12-30 | Backiaraj,Rajesh,Suganya | 8 | Invoice imported to Quickbook using zed axis tool and file location path checked. |  | 11 |  | 1
2017-01-02 | Backiaraj,Rajesh,Suganya | 8 | Export excel(invoice list) email structure worked for roots. |  | 11 |  | 1
2017-01-03 | Backiaraj,Rajesh,Suganya | 8 | Invoice list attachment in email and date format issue worked for roots |  | 11 |  | 1
2017-01-04 | Backiaraj,Rajesh,Suganya | 8 | Datatable issue and mail content changes worked and tested for roots |  | 11 |  | 1
2017-01-05 | Backiaraj,Rajesh,Suganya | 8 | Date format and excel structure issues worked for roots |  | 11 |  | 1
2017-01-06 | Backiaraj,Rajesh,Suganya | 8 | Completed and open order list table issue worked and tested for roots. |  | 11 |  | 1
2017-01-07 | Backiaraj,Rajesh,Suganya | 8 | online ordering flow tested and icon design issue worked. |  | 11 |  | 1
2017-01-09 | Backiaraj,Rajesh,Suganya | 8 | online order flow tested and issues (order date,address, auto save) worked for roots. |  | 11 |  | 1
2017-01-10 | Backiaraj,Rajesh,Suganya | 8 | print invoice, checkout, saved orders issue worked for roots. |  | 11 |  | 1
2017-01-11 | Backiaraj,Rajesh,Suganya | 8 | Order track view issue and excel export coloum hide issue worked for roots |  | 11 |  | 1
2017-01-12 | Backiaraj,Rajesh,Suganya | 8 | Order date format, po date format issues worked for roots |  | 11 |  | 1
2017-01-13 | Backiaraj,Rajesh,Suganya | 8 | Adding products(woven,hangtag,other and printed) changes worked for roots |  | 11 |  | 1
2017-01-16 | Backiaraj,Rajesh,Suganya | 8 | product list page,invoice paid and price changes worked for roots. |  | 11 |  | 1
2017-01-17 | Backiaraj,Rajesh,Suganya | 8 | woven,hangtags,printed and other products activate,deactivate issues worked and tested for roots. |  | 11 |  | 1
2017-01-18 | Backiaraj,Rajesh,Suganya | 8 | product image display in edit pages(woven,hangtag,printed and other),page redirect issue worked for roots. |  | 11 |  | 1
2017-01-19 | Backiaraj,Rajesh,Suganya | 8 | Product remain issue and delivery instruction(readonly) issue worked for roots |  | 11 |  | 1
2017-01-20 | Backiaraj,Rajesh,Suganya | 8 | Garment component issue, alertbox issue, po date(readonly),data upload validation issue worked for roots |  | 11 |  | 1
2017-01-30 | Backiaraj,Rajesh,Suganya | 8 | Production office dropdown,export invoice date picker and super admin login changes worked for roots. |  | 11 |  | 1
2017-01-31 | Backiaraj,Rajesh,Suganya | 8 | size maintenance alert box issue, saved order field set issues worked for roots |  | 11 |  | 1
2017-02-01 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Marks account(new URL) created. Quality of raw material page, product page changes worked for roots. |  | 11 |  | 1
2017-02-02 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Users(Jenny,Shirley,Mandy) created, common url changes, checkout and dashboard page changes, product images updated, Care and variable labes tab changes, printed,hangtag pages worked for marks |  | 11 |  | 1
2017-02-03 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Vendor list added in marks system. Hangtags, printed, allother(Add,edit,view,delete and autosave) changes, Header buttons(Prev,Next,Cancel) changes, Alertbox, Font icon changes, Checkout, Shopping cart form, Auto save form changes worked for marks login. Super admin login changes(dyanamic chain,default user adding,alertbox,fonticon,closeform issue) worked. |  | 11 |  | 1
2017-02-04 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Product description updated. Marks logo added. Heat Transfer prodct and order page changes worked. Ordering tab changes worked for care,variable,printed,hangtag and other product. Marks logo added in header. Season restriction removed. Item code added(care,variable,printed,hangtag,heartransfer and other) in all the tabs. |  | 11 |  | 1
2017-02-06 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Size code list added in marks. Add size functinality(qty per each size) changes, Order form(update,delete, view) changes, Quantity and season validation changes, Size code dropdown changes, size and color save changes worked for carelabels, variable, printed, hangtags, other products. Order flow(add,update,view and delete) worked for Heat Transfer for marks. |  | 11 |  | 1
2017-02-07 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Symbol(wash,bleach,iron,dry and tumble) list uploaded, Self-populating fields(P/O number, Delivery date, Style number) changes worked, Price sticker page changes(removing group,clor,price textbox) worked, Care instruction(symbols) changes worked in carelabel,updatedcarelabel,view and checkut, size code display changes worked for marks. |  | 11 |  | 1
2017-02-08 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Country of Origin list added, historical information inputting changes worked for heattransfer, production office issue worked for carelabels, marks ponumber label changes worked in checkout, product image view worked for care,rice sticker and checkout, max 7sizes validation worked in variable,printed, heattransfer, other products for marks |  | 11 |  | 1
2017-02-09 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Order flow(place order) changes workd in Carelabe,pricesticker,printed,hangtag,heattransfer and all other products. Viewsales order page changes worked, datatable worked in pending order list, Price sticker(saved order) change worked for marks. |  | 11 |  | 1
2017-02-10 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Product pack size updated in website, coordinator,artwork,production and delivery confirmation worked, mail template changes worked, artwork activation,rejection,error page template changes worked, printinvoice page changes and usermaintenance(type,region) dropdown remaining changes worked for marks. |  | 11 |  | 1
2017-02-13 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | User list added to website. Added Country Of Origin in french, Select at least one from the below validation message changes, fibre to fabric label changes, Still to complete button removed, changed Add style to Add size in all the pages, Season,size,quantity auto populate changes, Other products restiction(size,color) changes, delivery instruction page changes worked for marks. |  | 11 |  | 1
2017-02-14 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Auto populate size changes for other products, Size details table worked in update,view and checkout page, delivery instruction page changes, Size detail delete button change worked for marks. |  | 11 |  | 1
2017-02-15 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Auto save(aad and update) worked for care, price sticker, printed, hangtag, heattransfer and other. Size, color and quantity auto populate worked in other products. Quantity roundoff issue worked in all other and price sticker, Auto save cart changes worked for marks. |  | 11 |  | 1
2017-02-16 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | User list added to system. Auto populated size changes worked in savedcare,savepricestixker,savedprinted,savedheat and savedother products. Delivery instrction auto populated worked. Save Order and Auto save worked in all the pages for marks. |  | 11 |  | 1
2017-02-17 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Heat Transfer and Other Products size autopopulate issue worked, barcode max limit(12) change worked in pricesticker(add,update and autosave page). Remember me checkbox change worked in login page for marks. |  | 11 |  | 1
2017-02-18 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Remember me checkbox issue worked and updated in live, Size auto populate tested, issues fixed and changes updated in live. user list login checked. Phone number restriction removed in Usermaintenance page for marks. |  | 11 |  | 1
2017-02-20 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Size and quantity table worked in all view pages(open,completed,pending order list), Account and invoice login changes worked, Export and search invoice page added, Invoice export excel and mail attachment worked for marks. |  | 11 |  | 1
2017-02-21 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Size and Quantity autopopulated display issue(after adding in add to cart) worked care label, price sticker, printed label, heat transfer and other products. Max size 7 restriction for autopopulated size changes worked in printed label. Ordering flow(place order to delivery) changes worked for marks. |  | 11 |  | 1
2017-02-22 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Country of origin list updated, Main page product group reset worked, Select production region removed from all the pages, Ponumber, Style no, Barcode and seson restriction(max-15, allow special character) changed in all pages, Exclusive of Decoration removed, Barcode for each size worked in Price Sticker for marks. |  | 11 |  | 1
2017-02-23 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Selling price added to the products, Color dropdown changes worked for price stickers, Removed the products(not in season), Color list added tp system, Color drop down search worked,Remove region fromorderlist table and viewsalesorder for marks. |  | 11 |  | 1
2017-02-24 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Product price list updated to website, Color list added to the system, Color and Size dropdown alphabetical order change worked, Price sticker size details table change worked, Customer order number label change worked for marks. |  | 11 |  | 1
2017-02-27 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Production region added in all the pages, mail with price details changes worked, product group order rest worked in shopping cart, Delivery date and price field added in viewsalesorder page for marks.
2017-02-28 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Maximum sizes(7) issue worked in all the pages(care, printed, heattransfer,hangtag,price sticker and other products), Amend order list and update worked for all pages(amencare, amendprinted, amendheattransfer, amendhangtag, amendprice sticker and amend other products), Data table view changes worked in amendlist, completedorderlist and openorderlist.
2017-03-01 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Fabric composition list added to website, Ponumber design issue fixed, auto populated size changes uploaded and tested, Online ordering flow tested for marks.
2017-03-02 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Changed Price label as Value of Order,added $ sign in price, Deliver date and price alignment, Customer information and Order details label change, Grand total for price list in mail, Price table headings alignment changes, adding delivery date in mail change, changed Order ID as Order Summary worked for marks.
2017-03-03 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Upload artwork for price sticker worked, artwork approval and rejection mail worked for price sticker, delivery date default selection worked in deliveryinstruction page, orderstatus and open order datatable issue worked, delivery date design issue worked for marks.
2017-03-04 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Ponumber, Styleno, Season with singlecodes insertion issue worked for care, pricesticker, printed, heattransfer, hangtags and other products. Order ID changed as Order Summary with Ponuber for placeorder,confirm,artwork,production and delivery order in mail and changes tested for marks.
2017-03-06 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Amend order page worked for co ordinator login, Garment component issue in update and amend orders, podate issue in all view pages and print invoice, Barcode update in amend order, mail list from address issue, allother page quantity and add size issue worked and tested for marks.
2017-03-07 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Register username and forgot username form and mail worked, quantity textbox issue worked in update allother and amend all other, page redirection for back button worked in all amend order pages, amend order mail changes and Price sticker tab active issue worked in amend order list for marks.
2017-03-08 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Completed and open order export excel list worked, Region name added in completed,open,pending,confirmed and open order list, Changes tested and completed order datatable design issue worked, Size and quantity update issue worked in savedallother products for marks.
2017-03-10 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Care Label information table design issues worked in printinvoice page, region name and border issue worked in checkout and viewsalesorder page. Digits only and required field issue for quantity textbox worked in all pages(add,update and autosave), Barcode required issue worked in pricesticker page for marks.
2017-03-13 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Amend order edit page layout changed for care, price sticker, hangtag, heattransfer, printed and other products. Change password menu issue worked and mail to address issue worked in mail list page for marks.
2017-03-14 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Unique group site content alignment in mobile v iew issue, breadcrum isue, side menu issue worked for live site. Changes and design issues tested for marks.
2017-03-15 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Previous,Next button design issue worked in all the pages(care,printed,hangtag,heat transfer, allother priducts). Unnecessary style and functinalities removed from all the pages for marks. Unique group site tested in mobile view(6 plus)
2017-03-16 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Export invoice into an excel changes worked in account login, invoice list active, search invoive worked in account login, Remember me checkbox issue worked for marks.
2017-03-17 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Auto save and save order button issue worked for other products, Artwork status change issue for printed, heattransfer, hangtags and other products worked, Region and chain name issue in completed orders worked for marks.
2017-03-18 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Page redirect(dyanamic url) issue worked in completed, open, ordersummary and export invoice page. Online order flow tested for marks.
2017-03-20 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Online order flow(place order,confirm order, artwork approve,production and delivery) tested and issues worked for marks. Print invoice page and data table design issue worked for marks.
2017-03-21 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | storing a image in json format checked in subbrand maintenance page, delivery date issue worked in place order form and viewsales order page for marks.
2017-03-22 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Design issue (css file) worked for care ,printed, hangtag, heattransfer ,pricesticker and other products, logo Image changed in print invoice page for marks.
2017-03-23 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Amend order list issue, amend order update page worked for care, price sticker, hangtags, heattransfer and printed labels. Data table issue worked in amendorder list for marks.
2017-03-24 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Import file design checked, file upload restriction worked in dataupload menu. Alert message box layout changed in all the apge for marks.
2017-03-27 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Hangtag products added in the website, Country of origin(alphabetical)issue, Size dropdown order issue worked in all the pages. MOQ change worked for carelabel, pricesticker, hangtag, heattransfer,other product and printed labels, Garment Price decimal issue worked for marls.
2017-03-28 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Garment price textbox changes(allow upto two decimal place), Quantity issue in printinvoice page, Unit cost added in viewsalesorder, Submit button changed as Confirm for coordinator login worked for marks
2017-03-29 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Online order system flow document prepared. Care label MOQ change, garment price decimal point change, value of order(two decimal place) changes worked for marks.
2017-03-30 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Print function is worked in order view list for care labels,printed label, hangtag, heattransfer, pricesticker, other products and Garment Component label issue worked in printcheckout page for marks.
2017-03-31 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Care label MOQ change(250) worked in placeorder,update order and savecare pages, Garment price decimal point change, Garment price label change worked in checkout, viewsalesorder pages for marks.
2017-04-01 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Value of order(two decimal place) change worked in viewsales order page for care labels, printed label, hangtag, heattransfer, pricesticker and other products for marks.
2017-04-03 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Dashboard logo image, main image changes worked and Unit price and Order Value coloumn added, total row added for all the products in checkout page for marks.
2017-04-04 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Unit price and Order Value added in size table for all the productsin viewsalesorder page, Breadcrum change, expansion arrow change, button design issue worked for all the products for marks.
2017-04-05 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Email structure worked for all (place order, coordinator,artwork approve, reject, production and delivery), artwork uploaded file download issue worked in mail list for marks.
2017-04-06 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Finance login created, proforma invoice upload tab worked in finance login, delivery date worked in production login, tracking label before shipment worked in shipping login, delivery date requested change worked in all the pages for marks.
2017-04-07 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | New user(a5order) created in online order system, email flow changed (from place order to production), artwork resent mail structure worked, unique logo image changed for marks.
2017-04-10 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Artwork mail auto resent(cron job file) worked and uploaded in marks, proforma invoice uploaded status update and tracking label display in completed order page worked for marks.
2017-04-11 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Product link to customer link removed from product maintenance for all the labels, product to customer restriction removed in care labels, printed, hangtag, heattransfer,price sticker and other product for marks.
2017-04-12 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Proforma invoice auto resent mail(cronjob file) worked and checked, price detail table design issue worked, delivery date requested change worked in viewsales order page for marks.
2017-04-13 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Add size, save order, auto save changes worked in all update orders, Adding new user,customer,product,symbol,coutryof origin and size flow document prepared for marks.
2017-04-14 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Order tracking view arrow changes worked in viewsales order and Previous,Next button design issue worked in all the edit pages(care,printed,hangtag,heat transfer, allother priducts). for marks.
2017-04-15 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Size and quantity field required issue in update order worked, arrow issue in pendingorder list worked, artwork images and date details view page worked for marks.
2017-04-17 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Required field for size and quantity worked in all the saved order page, auto save function added in edit pages and mail structure worked for finance login for marks.
2017-04-18 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Save order button removed from create and edit order for all the products, $ sign added in garment price, two decimal place change worked for garment price, online order flow document updated for marks.
2017-04-19 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Customer service order confirmation, delivery date confirmation, uploading invoice to the system, finance payment confirmation, email with tracking information changes worked for marks.
2017-04-20 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Online order flow (order confirmation) mail changes worked, production confirmation mail flow changes, invoice upload for finance login worked for marks.
2017-04-21 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Online Order Procedure – BUILD (care labels,price sticker) and Online Order Procedure – PICK & PACK (printed labels, heattransfer, hangtags and other products) flow changed for marks.
2017-04-24 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Online order flow for care label,price sticker(option 1), printed, hangtag(option2) and pricesticker, printed(option 3) flow changed, customer service(coordinator) confirmation worked for marks.
2017-04-25 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Garment price change, add style change, size table change worked in amend orders for all products, Payment status(Paid/Not paid) column added in finance login for marks.
2017-04-26 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Finance order track view(prepared/approved) changes, Uploaded file column added in pending order, order status and confirmed order for marks.
2017-04-27 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Artwork and Invoice file column added in pendingorders, confiremed orders, completed orders, orderstatus and open orders page and data table alignment issue worked for marks.
2017-04-28 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Email template worked for purchase order, coordinator confirmation, artwork approval, delivery date confimation, invoice upload, payment confirmation and tracking label submit for marks.
2017-04-29 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Finance status and artwork status column added in order view table, Courier name field added in shipping, Order track view color changed for all the steps for marks.
2017-05-02 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Order status change worked in all the order list page, Garment price demicimal point issue, email address change, mail structure issue(all mails) worked for marks.
2017-05-03 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Mail list to address issue worked, mail system(build, pick&pack) added in mail list page, order track view(arrow) issue worked and $ sign added for garment price for marks.
2017-05-04 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Mail template design issue(line height, fontsize, fontcolor) issue worked, maillist popup design changed, order track view color and design changes worked for marks.
2017-05-04 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Mail template design issue(line height, fontsize, fontcolor) issue worked, maillist popup design changed, order track view color and design changes worked for marks.
2017-05-05 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Order track view issue(finance state) fixed, order track view arrow design issues worked, viewsales order status change issue and maillist layout change worked for marks.
2017-05-08 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | Cancel button page redirection changed in care,printed,hetatransfer,hangtags,pricesticker and all other products and mail list view (all mails) changed for marks.
2017-05-09 | Backiaraj,Rajesh,Suganya,Manimaran | 8 | View track order flow, arrow and responsive issue changes worked, artwork, finance pending order message(alert) label changed and orderstatus issue worked for marks.